## Tabelle1
Risk Occurrence |  |  |  | Risk Factor |  |  |  | Risk Impact
1 |  | 10 |  | 1 |  | 10 |  | 1 | 10
not likely |  | likely |  | Low |  | High |  | negligible | large
Risk ID | Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
1 | Time Planning | Totally wrong planned time | 5 | 4 | 3 | Systematically correcting Times | Nico
2 | Illness | Some Teammeber gets ill | 5 | 5 | 7 | All Teammembers should know every Part of the Project | Krissi
3 | No Internet | Internet connection is jammed | 5 | 7 | 4 | Local Development | Danny
4 | Missing Competences | Missing Competences for specific Tasks | 10 | 2 | 9 | Tutorials + Help by other Teams | Danny